## Original
GBC COURSE PLANNING TIMELINE - Spring 2020
|  | Final | Last Updated - 07/01/2019
Start | Finish | Task
| 2019-08-02 | SIS Operations rolls Spring 2019 to Spring 2020 & open Term Security. Upload for the web class schedules (internal use only), catalog (for Media Services) | SIS Ops
| 2019-08-02 | Start turning in book orders | Faculty
August 5 - Sept 7 |  | Dept Chairs plan classes to add, change & delete. Elko SS make additions, changes & deletions. DELETING UNWANTED CLASSES - VERY IMPORTANT. | Department Chairs/Faculty/Department Support Staff
| 2019-09-09 | Start advertising Registration Opening on website | Marketing
| 2019-09-09 | Centers start adds, changes & deletions. DELETING UNWANTED CLASSES - VERY IMPORTANT. | Centers
| 2019-09-20 | Preliminary Schedule - Department Chairs and Faculty submit to support staff all Spring 2020 courses. IAV originating classes to be entered, no room #s. Rooms decided at Center Directors' meeting. | Department Chairs/Faculty/Department Support Staff
| 2019-09-30 | Lecture Capture Requests submitted to IAV office | " "
| 2019-10-01 | ALL adds, changes and deletes NEED to be done by 10/15/19 | " "
2019-10-02 | 2019-10-03 | Center Director's to select IAV classes to receive. | Center Directors Meeting
2019-10-03 | 2019-10-09 | IAV receiving courses must be in PS by this date | Department Chairs/Faculty/Department Support Staff
| 2019-10-10 | ALL Spring Semester book orders due to GBC Bookstore. | " "
| 2019-10-10 | Dept reviews schedule. Changes made by Dept SS. The schedule should be complete. | Departments are 100% responsible for content
2019-10-10 | 2019-10-15 | Department support staff clean up in PS | " "
| 2019-10-15 | Final Schedule Due & deadline to add Spring classes. | " "
2019-10-16 | 2019-10-18 | 25 Live Data Prep and cleanup. PeopleSoft Class Schedule security will be closed | Computer Services
| 2019-10-16 | Any and all adds, changes, cancels (no deletes allowed)
2019-10-24 |  | Web Schedule is posted online. | Webmaster
| 2019-10-24 | Send out first part of printed schedule for editing | Marketing
2019-10-28 |  | Registration for Spring begins.
| 2019-12-02 | Download printed schedule | Marketing
2019-12-16 |  | Winter session classes begin
2020-01-21 |  | Regular term begins

## Copy
GBC COURSE PLANNING TIMELINE - Spring 2020
DRAFT
Start | Finish | Task | Notes
2019 May |  | SIS Operations runs Queries to update schedule.
| 2019-07-31 | Upload for the class schedules |  | Cynthia - 5/6/19 - Appr'd 5/8/19
| 2019-08-02 | SIS Operations rolls Spring 2019 to Spring 2020 & open Term Security. | SIS email only Elko SS
| 2019-08-02 | Faculty/Support Staff start turning in book orders. | Add to website | Jen & Frank - 5/6/19 Frank appv'd - 5/13/19 Jen approv'd - 5/16/19
August 5 - Sept 7 |  | Dept Chairs plan classes to add, change & delete. Elko SS make additions, changes & deletions. DELETING UNWANTED CLASSES - VERY IMPORTANT.
| 2019-09-09 | Center SS start adds, changes & deletions. DELETING UNWANTED CLASSES - VERY IMPORTANT. | SIS email Center's to start inputting classes
| 2019-09-20 | Cutoff for departments to submit to support staff all Spring 2020 courses.
| 2019-09-27 | IAV originating classes to be entered, no room #s. Rooms decided at Center Directors' meeting. | IAV originating classes must be added by now. | Bob - 5/16/19 Bob ok'd - 5/29/19
| 2019-09-30 | Lecture Capture Requests submitted to IAV office |  | Bob - 5/16/19 Bob ok'd - 5/29/19
| 2019-10-01 | Email DSS - ALL adds, changes and deletes NEED to be done 10/15/19 | Email DSS
2019-10-02 | 2019-10-03 | Center Director's to select IAV classes to receive. | Center Director Meeting | Bob - 5/16/19 Bob ok'd - 5/29/19
2019-10-03 | 2019-10-09 | IAV receiving courses must be in PS by this date | All IAV classes are due. | Bob - 5/16/19 Bob ok'd - 5/29/19
| 2019-10-10 | Spring Semester book orders due to GBC Bookstore. |  | Jen & Frank - 5/6/19 Frank apprv'd - 5/13/19 Jen apprv'd - 5/16/19
| 2019-10-10 | Dept reviews schedule. Changes made by Dept SS. The schedule should be complete. | Departments are 100% responsible for content.
2019-10-10 | 2019-10-15 | Department support staff clean up in PS
| 2019-10-15 | Deadline to add Spring classes. Classes added after this date may not be in the printed schedule, but will be on the web site. | SIS - Send out an email 5:00pm
2019-10-16 | 2019-10-18 | No PS access. 25 Live Data Prep and cleanup | 25Live optimization. | Donald & Sandra - 5/29/19 - both ok'd
| 2019-10-16 | Any and all adds, changes, cancels (no deletes allowed) need an add/change/cancel sheet now. | SIS - Send out an email 8:00am
2019-10-24 |  | Schedule is posted online.
2019-10-28 |  | Registration for Spring begins.
2019-11-04 |  | Media Services downloads schedule for hard copy. |  | Deleted these 2 per Kayla - 11/9/18
2019-12-02 |  | Schedule to arrive this week & will be sent out to all.
2019-12-16 |  | Winter session classes begin!
2020-01-21 |  | Regular term begins!