Great Basin College

TAACCCT Project Meeting

10:00 A.M. January 13th, 2015

Elko – Berg Hall Conference Room

TMCC – RDMT 315

- Project Director Update & Reminders

- PAR

- Please turn in to Heidi

- Quarterly Reports

- Due February 13th, please turn in by Jan. 30

- Scope of Work/Budget modification update

- Approved at regional level awaiting national approval

- Instructor Update

  - Math

- Working with retake and challenge exams

- Teaching two sections of physics 107

  - Millwright

- Lost a few students over break

- May receive a new student who currently has level 3 NCCER

- Working on form to compare credit hours to NCCER levels

- Contacted companies about onsite training

- Open house in shop offered to community Jan. 30

- Pathways Specialist Update

- Waiting for survey to be approved by the Nevada Mining Association

- Grant could benefit from skills certificate presentation at SCHS

  - Will ask Adriana to do this, to satisfy grant compliancy

  - Parent night also a possibility to stay compliant

- Instructional Design/Multimedia Specialist Update

- Artifacts being uploaded in Skills Commons

- Math course in progress

- New Start contract in progress

  - Purpose to mentor remedial math students

  - Mentor keeps in contact with student

  - Mentors keep in contact with instructors

  - Lisa receives reports on student progress

- Institutional Research Update

- Barb Walden working to give access to TMCC PeopleSoft

- This will allow proper data collection with time efficiency

- Working on grant documents for R-4

- Adult Learner Concierge Update

- Walk-in-Wednesdays still available

- Working on road trips throughout Nevada to inform communities of programs

- Marketing on electronic board during Summer

- Additional Department Updates

- Next Meeting Date

- TBA pending Doodle Poll results