Quarterly Progress Report Notes:

October 1 – December 31, 2016:

Affiliation contracts

Boulder City Hospital, for Pahrump students

Personnel

Nicole Sirotek started November 1st as new CNA Coordinator.

Equipment

With budget modification approval, purchase of SimMom was also approved.  SimMom was ordered and received for the Pahrump Nursing Lab.

MegaCode Kid was also ordered for Pahrump.

Elko IAV equipment retro still to be done.  Per Bob Hannu:  “We weren't able to come up with a date that didn't conflict with the extra Nursing classes, but my hope is that we can get it done some weekend in the next month.”

IAV Retro has been scheduled for October 13-14.  This has been done and a few other minor problems were encountered.  Bob Hannu is still dealing with CompView on those peripheral issues.  Operationally, the room should be all finished by November 5th.

Supplies

With the budget modification approval, Jacob Park has been able to order supplies for the Elko, Winnemucca and Pahrump VRC Center activities.

Curriculum Development

We’ve had six faculty participate in webinars offered by Nurse Tim.  This has been a worthwhile subscription and offered instructors great up-to-date information on all aspects of nursing education.  The subscription will expire in January.

CNA

A CNA class was conducted in Tonopah for the first time.  The lecture portion was done online with an Elko class.  Part-time instructors conducted lab skills and clinicals in Tonopah.  Results were a little disappointing:  5 students registered, 1 dropped, and 2 failed the course.  Future classes are unclear at this point.

Other

Information is being gathered to submit a request to DOL to extend Round 4 for six months (to April 2018).

Student Re-Cap:

Nursing	Fall 2015:  31 (20E, 5P, 6W) admitted, 6 (4E, 2P) withdrawn	= 25 Students

Fall 2016:  34 (23E, 5P, 6W) admitted				= 34 Students

CNA

Year 1:		Lovelock Spring 15 Class		  4 Students

Winnemucca Fall 15 Class		10 Students

Pahrump Fall 15 Class		12 Students

Year 2:		Elko Online Class Fall 15		11 Students

Winnemucca Spring 16 Class	11 Students

Pahrump Spring 16 Class		12 Students

Elko/Lovelock Online Spring 16	10 Students

Elko Online Summer 16		12 Students

Elko Online Summer 16		  9 Students

Winnemucca Summer 16		10 Students

Pahrump Summer 16			13 Students

Year 3:		Elko Online Fall 16			  5 Students	(ends 10/16/16)

Battle Mountain Fall 16		  4 Students	(ends 10/16/16)

Tonopah Fall 16			  2 Students	(ends 10/16/16)

Winnemucca Fall 16			10 Students	(ends 10/9/16)

Pahrump Fall 16			13 Students	(ends 11/3/16)

Elko Online Fall 16			15 Students	(ends 11/19/16)

Ely Online Fall 16			  5 Students	(ends 11/19/16)

Anticipated CNA classes Spring and Summer 2017:

Spring Elko Online/Other Rural Sites		20 Students

Spring Winnemucca				10 Students

Spring Pahrump				12 Students

Summer Pahrump				12 Students